## table_b
flat_id | work_description | discipline | level | area | trade | unique_value | boq_ref_number | boq_item_desc | unit_of_measure | unit_rate | budgeted_qantity | budgeted_cost | site_engineer | sub_contractor | labour_trade_1_name | labour_trade_1_manhours | labour_trade_2_name | labour_trade_2_manhours | labour_trade_3_name | labour_trade_3_manhours | budgeted_manhours | duration | productivity_rate | drawing_approval_status | material_delivered_status | progress | qaqc_engineer | ir_no | ir_no_id | date_of_inspection | time_of_inspection | rev | submitted | received | status_abbr | status | next_step | earned_value_cost | remaining_cost | earned_value_manhours | remaining_manhours | plan_start | plan_finish | predecessor | sucessor | ncr_if_any | snagging_if_any
A0M01 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2124 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 40000 | 10000
A0M01 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3897 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M01 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2223 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M01 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2705 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M01 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2158 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M01 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3576 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M01 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2505 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M01 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2538 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M01 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2399 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M01 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2901 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M01 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3583 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M01 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2977 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M01 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 2918 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M01 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 90 |  | 2598 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16000 | 4000
A0M01 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3406 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M01 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 90 |  | 3584 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A0M01 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2758 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M02 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 90 |  | 3030 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 40000 | 10000
A0M02 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2602 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M02 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3938 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M02 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 80 |  | 3999 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A0M02 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3737 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M02 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3240 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M02 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3194 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M02 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3447 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M02 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2368 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M02 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2197 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M02 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3690 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M02 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2443 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M02 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3851 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M02 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 2252 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M02 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3881 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M02 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2314 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M02 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 90 |  | 2071 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 18000 | 2000
A0M03 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3209 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 50000 | 0
A0M03 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2872 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M03 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3865 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M03 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2293 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M03 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2620 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M03 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2571 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M03 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3773 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M03 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2449 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M03 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2395 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M03 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3057 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A0M03 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2323 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M03 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3931 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A0M03 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 2510 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M03 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 90 |  | 2231 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M03 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2448 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M03 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3025 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M03 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3056 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M04 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3893 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 40000 | 10000
A0M04 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3212 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M04 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3781 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M04 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2381 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M04 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3897 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M04 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2262 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A0M04 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2908 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M04 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3265 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M04 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2069 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 20000 | 0
A0M04 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3481 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M04 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3902 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M04 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3248 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M04 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 2992 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M04 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3460 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M04 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2934 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M04 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2353 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M04 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2425 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M05 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3253 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 40000 | 10000
A0M05 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2890 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M05 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2571 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M05 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 90 |  | 2636 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M05 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2615 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16000 | 4000
A0M05 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3857 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M05 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3664 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M05 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3089 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M05 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2037 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 20000 | 0
A0M05 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3743 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M05 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2734 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M05 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2903 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M05 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3820 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M05 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 80 |  | 3961 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A0M05 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2830 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M05 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3178 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M05 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2785 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M06 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2270 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 40000 | 10000
A0M06 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2255 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M06 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2111 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M06 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3518 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M06 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3601 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M06 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3003 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M06 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2403 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M06 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3003 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M06 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2672 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M06 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3544 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A0M06 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2603 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M06 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2834 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M06 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3214 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M06 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 2979 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M06 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3228 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M06 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3191 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M06 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2423 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M07 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3528 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 40000 | 10000
A0M07 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 80 |  | 3981 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M07 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3344 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M07 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3020 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 20000 | 0
A0M07 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2873 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M07 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3774 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M07 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3301 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M07 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3531 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M07 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 3655 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M07 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3666 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M07 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2034 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 20000 | 0
A0M07 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3773 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M07 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3070 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M07 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 90 |  | 3280 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A0M07 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3781 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M07 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3903 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M07 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2809 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M08 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3027 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 40000 | 10000
A0M08 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2621 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M08 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3103 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M08 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2080 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 20000 | 0
A0M08 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2018 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 20000 | 0
A0M08 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3729 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M08 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 80 |  | 3974 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M08 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3010 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M08 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 3103 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M08 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2448 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M08 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3158 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M08 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3229 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M08 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 80 |  | 3976 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A0M08 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3798 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M08 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2305 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M08 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 90 |  | 2784 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M08 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3615 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M09 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2392 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 40000 | 10000
A0M09 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2131 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M09 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3533 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M09 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2840 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M09 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2765 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M09 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3586 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M09 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3211 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M09 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3673 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M09 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2048 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 20000 | 0
A0M09 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2440 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M09 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3496 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M09 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2990 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M09 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3864 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M09 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 90 |  | 2288 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M09 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2496 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M09 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2772 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M09 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3609 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M10 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 90 |  | 3793 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 40000 | 10000
A0M10 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3457 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M10 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2567 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M10 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3191 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M10 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3362 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M10 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2307 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M10 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3557 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M10 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2459 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M10 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2807 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M10 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3305 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M10 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 90 |  | 3292 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A0M10 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3762 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A0M10 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3695 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M10 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3822 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M10 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3851 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M10 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3160 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M10 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 90 |  | 3602 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M11 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 90 |  | 3312 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 40000 | 10000
A0M11 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3005 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M11 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3339 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M11 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 2842 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M11 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3547 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M11 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3639 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M11 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3101 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M11 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3940 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M11 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 3763 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M11 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3222 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M11 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2732 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M11 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3258 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M11 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3837 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M11 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3331 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M11 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 80 |  | 3969 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 8000 | 2000
A0M11 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2046 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M11 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 90 |  | 3286 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M12 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2706 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 40000 | 10000
A0M12 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2090 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 38000 | 0
A0M12 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3633 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M12 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3329 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M12 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2416 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M12 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2565 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M12 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3454 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M12 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3681 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M12 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2699 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M12 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3522 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M12 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2477 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M12 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2250 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M12 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3497 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M12 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 90 |  | 3874 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M12 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2863 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M12 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2279 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M12 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3916 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M13 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2599 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 40000 | 10000
A0M13 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3437 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M13 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2286 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M13 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3724 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M13 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3671 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M13 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2813 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M13 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3219 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M13 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2696 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M13 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2136 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M13 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2611 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M13 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 3773 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M13 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2725 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M13 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3477 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M13 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 2626 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M13 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2570 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M13 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 3763 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M13 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 2603 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M14 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 2544 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 40000 | 10000
A0M14 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2602 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M14 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3849 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M14 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3763 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M14 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2853 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M14 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3397 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M14 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2019 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 38000 | 0
A0M14 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3683 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M14 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 3206 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 20000 | 0
A0M14 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3065 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A0M14 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2801 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M14 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2001 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 12000 | 0
A0M14 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 2445 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M14 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3085 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M14 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3680 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M14 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2785 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M14 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3887 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M15 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 100 |  | 3170 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 40000 | 10000
A0M15 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2075 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 38000 | 0
A0M15 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2868 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M15 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3517 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M15 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2047 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M15 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3871 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M15 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3901 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M15 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3618 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M15 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 3941 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M15 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3943 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M15 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 90 |  | 2716 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M15 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2693 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M15 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 2127 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M15 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 2940 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M15 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3281 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M15 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 100 |  | 2097 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 20000 | 0
A0M15 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 100 |  | 3809 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M16 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 50000 | [13 empty] | 80 |  | 3995 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 40000 | 10000
A0M16 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3061 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M16 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2783 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M16 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 20000 | [13 empty] | 100 |  | 3076 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M16 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 80 |  | 3968 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A0M16 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2727 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M16 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3900 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M16 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2925 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M16 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 20000 | [13 empty] | 100 |  | 2463 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M16 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2097 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 12000 | 0
A0M16 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 20000 | [13 empty] | 100 |  | 2787 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A0M16 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2682 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M16 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 20000 | [13 empty] | 100 |  | 3453 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M16 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 20000 | [13 empty] | 100 |  | 3058 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M16 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3145 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M16 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 20000 | [13 empty] | 90 |  | 2774 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16000 | 4000
A0M16 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 20000 | [13 empty] | 90 |  | 3069 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M17 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2996 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M17 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2357 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M17 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3731 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M17 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2519 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M17 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2897 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M17 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2897 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M17 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2287 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M17 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2992 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M17 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2792 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M17 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3144 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M17 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3344 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M17 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3995 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A0M17 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2773 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M17 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3640 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M17 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2190 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M17 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3449 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M17 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3948 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M18 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2164 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 36000 | 9000
A0M18 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3078 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M18 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2348 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M18 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3180 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M18 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2594 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M18 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2940 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M18 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3109 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M18 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2516 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M18 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2539 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M18 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2084 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 12000 | 0
A0M18 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3077 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M18 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2010 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 12000 | 0
A0M18 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2882 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M18 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 2636 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M18 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2328 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M18 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 2320 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16200 | 1800
A0M18 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2180 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M19 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2317 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A0M19 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2870 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M19 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3944 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M19 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3689 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M19 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2714 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M19 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3262 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A0M19 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2421 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M19 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2950 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A0M19 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2877 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M19 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2066 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 12000 | 0
A0M19 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 2281 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M19 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3870 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M19 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 90 |  | 2216 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M19 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 3248 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M19 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3465 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M19 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3656 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M19 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2505 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M20 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 80 |  | 3965 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 36000 | 9000
A0M20 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3626 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M20 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2603 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M20 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 80 |  | 3964 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M20 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2046 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M20 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2859 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M20 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3879 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M20 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3824 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M20 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2226 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M20 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3503 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M20 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2147 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M20 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2843 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M20 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2760 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M20 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2591 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M20 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2191 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M20 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3180 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M20 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3763 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M21 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3738 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A0M21 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3178 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M21 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3269 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M21 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2955 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M21 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3674 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M21 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3030 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M21 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2522 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M21 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3400 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M21 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 80 |  | 3992 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M21 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3751 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M21 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3168 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M21 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2184 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M21 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3531 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M21 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3834 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M21 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2160 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M21 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2721 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M21 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2026 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 18000 | 0
A0M22 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2740 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A0M22 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3602 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M22 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2334 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M22 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 3644 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M22 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2826 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M22 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2339 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M22 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3332 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M22 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2106 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A0M22 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2420 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16200 | 1800
A0M22 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3786 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M22 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3525 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M22 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2208 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 12000 | 0
A0M22 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 80 |  | 3999 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M22 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2845 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M22 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2645 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M22 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2890 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M22 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3018 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M23 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2617 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A0M23 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3364 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M23 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3527 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M23 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 3860 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M23 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2449 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A0M23 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3474 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M23 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2273 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M23 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3293 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M23 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2105 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M23 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2098 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 10800 | 1200
A0M23 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3309 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M23 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3045 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M23 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3839 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M23 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3104 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M23 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3792 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M23 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2239 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M23 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3005 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M24 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3691 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A0M24 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3040 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M24 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3097 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M24 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3539 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M24 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3883 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M24 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2953 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M24 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3657 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M24 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2915 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M24 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3583 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M24 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2910 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M24 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2538 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M24 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3064 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M24 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2712 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M24 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2642 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M24 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2779 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M24 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 3546 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M24 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3096 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M25 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2703 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M25 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 80 |  | 3988 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M25 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3041 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M25 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2981 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M25 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2458 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M25 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3839 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M25 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2781 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M25 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3349 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M25 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2196 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M25 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2146 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M25 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3749 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M25 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3832 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M25 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2727 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M25 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2558 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M25 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3542 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M25 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3640 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M25 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3499 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M26 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2284 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M26 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2722 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M26 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3307 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M26 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 2720 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16200 | 1800
A0M26 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3047 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M26 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2275 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M26 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2617 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M26 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3551 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M26 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2833 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M26 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2494 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A0M26 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3261 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M26 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2360 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M26 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2124 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M26 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3324 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M26 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2379 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M26 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2090 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 18000 | 0
A0M26 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3645 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M27 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2606 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 36000 | 9000
A0M27 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2085 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 38000 | 0
A0M27 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2465 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M27 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 3827 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M27 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3519 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M27 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3777 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M27 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3936 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M27 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3214 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M27 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3129 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M27 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2181 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A0M27 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3650 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M27 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2105 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M27 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3801 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M27 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2626 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M27 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3235 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M27 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3948 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M27 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3847 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M28 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3383 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 36000 | 9000
A0M28 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3676 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M28 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3507 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M28 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2479 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M28 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3874 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M28 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2694 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M28 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3120 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 38000 | 0
A0M28 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2043 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9000 | 1000
A0M28 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2276 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M28 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3380 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A0M28 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2261 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M28 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3425 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M28 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3037 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M28 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 2987 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M28 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3063 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M28 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2705 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M28 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2182 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M29 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2343 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M29 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3916 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M29 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2003 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 34200 | 3800
A0M29 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2052 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 18000 | 0
A0M29 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3620 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 20000 | 0
A0M29 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2590 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M29 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3714 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M29 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3305 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M29 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3513 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M29 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3713 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M29 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 80 |  | 3970 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M29 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3491 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M29 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2145 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M29 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3342 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M29 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2858 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M29 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2653 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M29 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3782 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A0M30 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 80 |  | 3969 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 36000 | 9000
A0M30 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3881 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M30 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 80 |  | 3956 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M30 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2185 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M30 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3200 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 20000 | 0
A0M30 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2136 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M30 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3145 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M30 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3583 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M30 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2378 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M30 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3001 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M30 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3137 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M30 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2255 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M30 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 80 |  | 3982 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M30 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2797 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M30 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3360 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A0M30 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2246 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M30 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2674 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M31 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3409 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M31 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2361 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M31 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2789 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M31 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2635 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M31 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3126 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M31 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3727 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A0M31 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3745 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M31 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2628 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M31 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2671 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M31 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3871 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M31 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3295 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M31 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3140 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M31 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3355 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M31 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 2033 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16200 | 1800
A0M31 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2893 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M31 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 3341 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M31 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3615 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M32 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3411 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A0M32 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3470 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M32 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 80 |  | 3975 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M32 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3281 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M32 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3608 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M32 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3372 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M32 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2792 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M32 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2103 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M32 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2863 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M32 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2029 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 12000 | 0
A0M32 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2721 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M32 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3100 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M32 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2298 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M32 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2997 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M32 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3500 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A0M32 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2405 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M32 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2944 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M33 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3665 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 36000 | 9000
A0M33 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 2856 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M33 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2129 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M33 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2486 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M33 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3866 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A0M33 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3596 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M33 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3923 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M33 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3132 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M33 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3306 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M33 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2862 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M33 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3458 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M33 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2987 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M33 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2996 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M33 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3639 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M33 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3170 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M33 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 2524 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A0M33 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3010 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M34 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3223 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M34 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2647 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M34 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3773 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M34 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3598 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M34 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3055 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M34 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3718 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M34 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3600 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M34 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2661 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M34 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2993 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M34 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3775 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M34 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2837 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M34 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3760 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M34 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2678 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M34 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 3598 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M34 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2189 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M34 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3799 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M34 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3067 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M35 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2755 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A0M35 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 2602 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M35 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3230 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M35 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2167 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M35 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2141 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M35 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3732 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M35 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3786 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M35 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3729 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M35 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2310 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M35 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3063 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M35 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2791 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M35 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2941 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M35 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3184 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M35 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3492 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M35 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3609 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M35 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3655 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M35 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3056 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M36 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2744 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A0M36 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2683 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M36 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 80 |  | 3959 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M36 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2391 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M36 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3670 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A0M36 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2118 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M36 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2717 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M36 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2557 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M36 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2527 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M36 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2051 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 10800 | 1200
A0M36 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3843 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M36 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3990 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A0M36 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2651 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M36 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2786 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M36 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3751 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M36 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3552 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M36 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3310 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M37 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2914 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M37 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3919 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M37 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3433 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M37 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2292 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M37 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2057 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 20000 | 0
A0M37 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2989 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M37 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2460 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M37 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2340 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M37 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2341 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M37 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3304 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M37 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2464 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M37 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2231 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M37 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3873 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M37 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3423 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M37 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2737 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M37 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 3536 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M37 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2324 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M38 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 80 |  | 3968 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 36000 | 9000
A0M38 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 80 |  | 3987 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M38 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2737 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M38 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2433 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M38 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3447 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A0M38 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2057 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 10000 | 0
A0M38 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3804 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M38 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2931 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M38 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3235 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M38 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2142 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A0M38 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 2781 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M38 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3131 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M38 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2218 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M38 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2592 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M38 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2874 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M38 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3789 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M38 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3432 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M39 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2424 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M39 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2240 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M39 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3691 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M39 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 80 |  | 3973 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M39 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2479 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M39 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3787 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M39 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2153 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M39 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2721 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M39 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2032 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 18000 | 0
A0M39 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 80 |  | 3985 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A0M39 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3913 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M39 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3392 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M39 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2903 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M39 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3164 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M39 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3663 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M39 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2967 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M39 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2828 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M40 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3359 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 36000 | 9000
A0M40 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3945 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M40 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2078 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 34200 | 3800
A0M40 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2753 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M40 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3598 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A0M40 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2484 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M40 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3260 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M40 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3724 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M40 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3189 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M40 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3738 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M40 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2830 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M40 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3366 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M40 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2933 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M40 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2315 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M40 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2249 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M40 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3931 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M40 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2712 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M41 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3548 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A0M41 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3141 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M41 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2184 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M41 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2489 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M41 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3929 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M41 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3485 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M41 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2339 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M41 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2906 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M41 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2181 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M41 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2493 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M41 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2829 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M41 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2927 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M41 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2079 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 18000 | 0
A0M41 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2904 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M41 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3806 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M41 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3830 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M41 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2948 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M42 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3640 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M42 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3568 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M42 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2683 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M42 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3857 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M42 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3502 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M42 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 80 |  | 3960 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 8000 | 2000
A0M42 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3379 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M42 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2834 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A0M42 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3080 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M42 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2129 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M42 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 2326 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M42 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3223 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A0M42 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 90 |  | 2869 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M42 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2535 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M42 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2392 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M42 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3222 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M42 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3116 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M43 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3825 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A0M43 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3332 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M43 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2271 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M43 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2507 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M43 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2743 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M43 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2087 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 10000 | 0
A0M43 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3566 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A0M43 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2041 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 10000 | 0
A0M43 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3916 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M43 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3741 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M43 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 80 |  | 3993 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M43 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2538 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A0M43 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 90 |  | 2544 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M43 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 80 |  | 3961 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M43 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2923 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A0M43 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3547 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M43 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3514 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M44 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3480 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M44 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3522 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M44 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2705 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A0M44 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 2626 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M44 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3826 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M44 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3231 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A0M44 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3641 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M44 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2576 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M44 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2232 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M44 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3036 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M44 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3067 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M44 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3898 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M44 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3477 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M44 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 90 |  | 2559 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M44 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2015 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9000 | 1000
A0M44 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2714 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M44 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3692 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A0M45 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2648 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A0M45 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2358 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M45 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 80 |  | 3998 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M45 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3692 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M45 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3648 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16000 | 4000
A0M45 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3766 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M45 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2009 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 38000 | 0
A0M45 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2107 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M45 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3084 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M45 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3289 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M45 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2897 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M45 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3901 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A0M45 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3482 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M45 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2104 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M45 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3130 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M45 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2551 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M45 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2023 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 18000 | 0
A0M46 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3647 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M46 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2653 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A0M46 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2716 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A0M46 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3343 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M46 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3378 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M46 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3474 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M46 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2231 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A0M46 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3159 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M46 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3033 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M46 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3327 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A0M46 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3608 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M46 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2735 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A0M46 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2558 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M46 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2014 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 18000 | 0
A0M46 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3618 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A0M46 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3371 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M46 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3525 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M47 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3699 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A0M47 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2148 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M47 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2000 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 34200 | 3800
A0M47 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3024 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M47 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2624 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A0M47 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3503 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M47 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2199 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M47 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3458 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M47 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2775 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M47 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3110 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A0M47 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 90 |  | 3017 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M47 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3930 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M47 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 80 |  | 3952 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M47 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3627 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M47 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3198 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M47 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2216 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M47 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3769 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M48 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2262 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A0M48 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2630 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A0M48 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2664 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A0M48 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 3147 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A0M48 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3088 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A0M48 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2355 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A0M48 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2222 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M48 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2326 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M48 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2770 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M48 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3288 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A0M48 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3271 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M48 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3616 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A0M48 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3485 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M48 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2433 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M48 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3479 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M48 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2539 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M48 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2892 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M49 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2117 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A0M49 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2013 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 38000 | 0
A0M49 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2118 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M49 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2238 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M49 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2671 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A0M49 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3492 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A0M49 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3899 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A0M49 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3888 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M49 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3010 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M49 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3684 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M49 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3641 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M49 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2406 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A0M49 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2739 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M49 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 80 |  | 3964 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M49 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2748 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M49 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 90 |  | 3318 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M49 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3747 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A0M50 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3427 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A0M50 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2002 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 38000 | 0
A0M50 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 80 |  | 3980 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A0M50 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 3869 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M50 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3367 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M50 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3361 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M50 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2094 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 38000 | 0
A0M50 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3408 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A0M50 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2358 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M50 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2055 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 12000 | 0
A0M50 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2147 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M50 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2863 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A0M50 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2693 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M50 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2821 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A0M50 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2231 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M50 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2749 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M50 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 80 |  | 3989 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A0M51 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2647 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A0M51 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3126 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M51 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2904 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A0M51 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 90 |  | 2565 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A0M51 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3830 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A0M51 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2670 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A0M51 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2680 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A0M51 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2886 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A0M51 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3746 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A0M51 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3268 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A0M51 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2185 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M51 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3115 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A0M51 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3575 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M51 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2905 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M51 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2323 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A0M51 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 2825 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A0M51 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2947 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A0M52 | Final Fix aluminium and Façade work | ARC | 0M | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3309 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A0M52 | MEP 3rd Fix Electrical | MEP | 0M | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3196 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A0M52 | MEP 3rd Fix Mechanical | MEP | 0M | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2039 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 38000 | 0
A0M52 | Joinery Final Fix Doors | ARC | 0M | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3755 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M52 | Final Paint Coat | ARC | 0M | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3847 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A0M52 | Marble Threshold Final Fix | ARC | 0M | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3338 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A0M52 | MEP 3rd Fix Plumping | MEP | 0M | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3468 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A0M52 | Tiles Final Fix Wet Area | ARC | 0M | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2160 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M52 | False ceiling Final Fix Wet Area | ARC | 0M | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3840 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A0M52 | Mirror Final Fix | ARC | 0M | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 80 |  | 3994 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A0M52 | Vanity Counter Final Fix | ARC | 0M | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2472 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A0M52 | Glass Shower Partition Final fix | ARC | 0M | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3133 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A0M52 | Joinery Final Fix Laundry | ARC | 0M | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3204 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 18000 | 0
A0M52 | Joinery Final Fix Kitchen | ARC | 0M | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2925 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A0M52 | Tiles Final Fix Dry Area | ARC | 0M | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2105 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A0M52 | Joinery Final Fix wardrobe | ARC | 0M | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3602 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A0M52 | False ceiling Final Fix Dry Area | ARC | 0M | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3614 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A101 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3260 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A101 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 2897 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A101 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2950 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A101 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3593 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A101 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2483 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A101 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3664 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A101 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2605 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A101 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2465 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A101 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2576 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A101 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2055 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 12000 | 0
A101 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2455 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A101 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3555 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A101 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 2787 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A101 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3502 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A101 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3567 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A101 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3724 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A101 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3040 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A102 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3254 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 36000 | 9000
A102 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3589 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A102 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2691 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A102 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3110 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A102 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2204 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 20000 | 0
A102 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 80 |  | 3963 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 8000 | 2000
A102 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3601 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A102 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2523 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A102 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2114 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A102 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2412 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A102 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2320 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 18000 | 0
A102 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2347 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A102 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3501 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A102 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2447 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A102 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3014 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A102 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3843 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A102 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2859 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A103 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2006 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 45000 | 0
A103 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3635 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A103 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3342 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A103 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 2461 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A103 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 80 |  | 3985 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A103 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3400 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A103 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2202 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 38000 | 0
A103 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2571 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A103 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3767 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A103 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2200 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 10800 | 1200
A103 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 3118 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A103 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3096 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A103 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 90 |  | 2700 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A103 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 2970 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A103 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2536 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A103 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 100 |  | 3432 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A103 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2498 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A104 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3260 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A104 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2425 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A104 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2850 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A104 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 100 |  | 3565 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A104 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2088 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 18000 | 2000
A104 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2449 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A104 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2186 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A104 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3804 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A104 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3899 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A104 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2636 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A104 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 100 |  | 2195 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A104 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2483 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A104 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 100 |  | 3911 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A104 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 100 |  | 3500 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A104 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2310 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A104 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A104 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3336 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A105 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2409 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A105 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2633 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A105 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2726 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A105 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A105 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3942 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A105 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2099 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 10000 | 0
A105 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2348 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A105 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3123 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A105 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2087 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 18000 | 0
A105 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2838 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A105 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A105 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2928 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A105 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A105 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A105 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2401 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A105 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A105 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2854 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A106 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2198 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A106 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3935 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A106 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2633 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A106 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A106 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3155 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A106 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2348 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A106 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3875 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A106 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3296 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A106 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2594 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A106 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3682 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A106 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 |  | 3657 | [7 empty] | Not Submitted |  | 0 | 18000
A106 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2425 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A106 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 |  | 2999 | [7 empty] | Not Submitted |  | 0 | 18000
A106 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 |  | 2579 | [7 empty] | Not Submitted |  | 0 | 18000
A106 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3467 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A106 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 |  | 3963 | [7 empty] | Not Submitted |  | 0 | 18000
A106 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3031 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A107 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3043 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A107 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2648 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A107 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3625 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A107 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 |  | 3733 | [7 empty] | Not Submitted |  | 0 | 18000
A107 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2082 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 18000 | 2000
A107 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3605 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A107 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2693 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A107 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2422 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A107 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3564 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A107 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2894 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A107 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 |  | 3149 | [7 empty] | Not Submitted |  | 0 | 18000
A107 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3728 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A107 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 |  | 3103 | [7 empty] | Not Submitted |  | 0 | 18000
A107 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 |  | 2009 | [7 empty] | Not Submitted |  | 0 | 18000
A107 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2173 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A107 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 |  | 3428 | [7 empty] | Not Submitted |  | 0 | 18000
A107 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 80 |  | 3980 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A108 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3728 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A108 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2364 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A108 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3072 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A108 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 |  | 2789 | [7 empty] | Not Submitted |  | 0 | 18000
A108 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3661 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A108 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2483 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A108 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3885 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A108 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2989 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A108 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3227 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A108 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3737 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A108 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 |  | 3329 | [7 empty] | Not Submitted |  | 0 | 18000
A108 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3938 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A108 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 |  | 3808 | [7 empty] | Not Submitted |  | 0 | 18000
A108 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 |  | 2015 | [7 empty] | Not Submitted |  | 0 | 18000
A108 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3570 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A108 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 |  | 2163 | [7 empty] | Not Submitted |  | 0 | 18000
A108 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2175 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A109 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3176 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A109 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 80 |  | 3968 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 30400 | 7600
A109 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3763 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A109 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A109 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3398 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A109 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2824 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A109 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3360 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A109 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2909 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A109 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3807 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A109 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2735 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A109 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A109 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2556 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A109 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A109 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A109 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3230 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A109 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A109 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2906 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A110 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3604 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 36000 | 9000
A110 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2714 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A110 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2252 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A110 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A110 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2134 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A110 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2490 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A110 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2663 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A110 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3633 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A110 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 80 |  | 3952 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A110 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3438 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A110 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A110 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3116 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A110 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A110 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A110 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3089 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A110 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A110 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2009 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16200 | 1800
A111 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3944 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A111 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3515 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A111 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2910 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A111 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A111 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3372 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A111 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2814 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A111 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3694 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A111 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2180 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A111 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2155 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A111 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3021 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A111 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A111 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3027 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A111 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A111 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A111 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2912 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A111 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A111 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2269 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A112 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3732 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A112 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3542 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A112 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2100 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A112 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A112 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3249 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A112 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2260 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A112 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2502 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A112 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2260 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A112 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2620 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 18000 | 0
A112 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2787 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A112 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A112 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2740 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A112 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A112 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A112 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3438 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A112 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A112 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3337 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A113 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 80 |  | 3956 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 36000 | 9000
A113 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3491 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A113 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3363 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A113 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A113 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3242 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A113 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3357 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A113 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3765 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A113 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3797 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A113 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3712 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A113 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2924 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A113 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A113 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3966 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A113 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A113 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A113 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2203 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 10000 | 0
A113 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A113 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 80 |  | 3984 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A114 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3052 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A114 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3098 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A114 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2416 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A114 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A114 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2479 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A114 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3707 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A114 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3160 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A114 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2327 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A114 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2605 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A114 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3349 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A114 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A114 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3595 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A114 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A114 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A114 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2781 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A114 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A114 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3428 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A115 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2146 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 36000 | 9000
A115 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3885 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A115 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2436 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A115 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A115 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3062 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A115 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2340 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A115 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3522 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A115 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3716 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A115 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2029 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16200 | 1800
A115 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3198 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A115 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A115 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3373 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A115 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A115 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A115 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2903 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A115 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A115 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3289 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A116 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3575 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 36000 | 9000
A116 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3387 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A116 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3287 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A116 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A116 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2608 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A116 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3654 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A116 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3803 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A116 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3890 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A116 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3322 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A116 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2423 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A116 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A116 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3430 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A116 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A116 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A116 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3484 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A116 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A116 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3758 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A117 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3417 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A117 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3114 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A117 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3718 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A117 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A117 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2233 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A117 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2353 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A117 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2676 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A117 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3257 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A117 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3863 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A117 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3250 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A117 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A117 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3937 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A117 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A117 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A117 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3045 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A117 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A117 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2810 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A118 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2016 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 40500 | 4500
A118 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2779 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A118 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2305 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A118 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A118 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3030 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A118 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2328 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A118 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3113 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A118 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3837 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A118 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3881 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A118 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3682 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A118 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A118 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3031 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A118 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A118 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A118 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2799 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A118 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A118 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2598 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A119 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2006 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 45000 | 0
A119 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3872 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A119 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 2123 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A119 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A119 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2585 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A119 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2769 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A119 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3345 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A119 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2509 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A119 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3858 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A119 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3353 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A119 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A119 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2796 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A119 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A119 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A119 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2567 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A119 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A119 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2848 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A120 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3876 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A120 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3701 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A120 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2650 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A120 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A120 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2765 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A120 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3917 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A120 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2236 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A120 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2242 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A120 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2106 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A120 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2196 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A120 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A120 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3481 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A120 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A120 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A120 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 2249 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A120 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A120 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2001 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 18000 | 0
A121 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3578 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A121 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2623 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A121 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2037 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 38000 | 0
A121 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A121 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3526 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A121 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3535 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A121 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2345 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A121 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3003 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A121 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2880 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A121 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3138 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A121 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A121 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3277 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A121 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A121 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A121 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3439 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A121 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A121 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3827 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A122 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2971 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 36000 | 9000
A122 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3646 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A122 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3163 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A122 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A122 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2983 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A122 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3487 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A122 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3050 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A122 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3186 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A122 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3856 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A122 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3426 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A122 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A122 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2335 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A122 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A122 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A122 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2542 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A122 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A122 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2780 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A123 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2770 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A123 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2107 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A123 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2446 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A123 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A123 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3600 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A123 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2892 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A123 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2119 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A123 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3733 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A123 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2609 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A123 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2026 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 12000 | 0
A123 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A123 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2687 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A123 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A123 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A123 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3543 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A123 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A123 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2036 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 18000 | 0
A124 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2201 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 45000 | 0
A124 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2645 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A124 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2540 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A124 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A124 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2860 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A124 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3618 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A124 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2739 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A124 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2507 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A124 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2476 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A124 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3572 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A124 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A124 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3155 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A124 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A124 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A124 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3242 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A124 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A124 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2791 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A125 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3755 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A125 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2524 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A125 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3835 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A125 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A125 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2651 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A125 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3721 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A125 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3409 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A125 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3902 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 8000 | 2000
A125 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2568 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A125 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3329 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A125 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A125 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2105 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A125 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A125 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A125 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3517 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A125 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A125 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3311 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A126 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3408 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 36000 | 9000
A126 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3940 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A126 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3560 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 30400 | 7600
A126 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A126 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3374 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A126 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2190 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A126 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3622 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A126 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3636 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A126 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2913 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A126 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3254 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A126 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A126 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2198 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A126 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A126 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A126 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2543 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A126 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A126 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3089 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A127 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3179 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A127 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3490 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A127 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3206 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 38000 | 0
A127 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A127 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3355 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A127 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3793 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A127 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2370 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A127 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3770 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A127 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2369 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A127 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2161 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A127 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A127 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2979 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A127 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A127 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A127 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2054 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 10000 | 0
A127 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A127 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2945 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A128 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3745 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A128 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3235 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A128 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3351 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A128 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A128 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2537 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A128 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3890 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A128 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2425 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A128 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3654 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A128 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2528 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A128 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2380 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A128 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A128 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3980 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A128 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A128 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A128 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 80 |  | 3995 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 8000 | 2000
A128 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A128 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3700 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A129 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2234 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A129 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3445 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 30400 | 7600
A129 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3314 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A129 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 |  | 3415 | [7 empty] | Not Submitted |  | 0 | 18000
A129 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2065 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 20000 | 0
A129 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3097 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A129 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2440 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A129 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3885 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A129 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3754 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A129 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2801 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A129 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 |  | 2631 | [7 empty] | Not Submitted |  | 0 | 18000
A129 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3630 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A129 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 |  | 3691 | [7 empty] | Not Submitted |  | 0 | 18000
A129 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 |  | 3328 | [7 empty] | Not Submitted |  | 0 | 18000
A129 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3459 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A129 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 |  | 2438 | [7 empty] | Not Submitted |  | 0 | 18000
A129 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3772 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A130 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3069 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A130 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3606 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A130 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3498 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A130 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 |  | 3413 | [7 empty] | Not Submitted |  | 0 | 18000
A130 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3579 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A130 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3002 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A130 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2290 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A130 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2500 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A130 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3845 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A130 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3895 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A130 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 |  | 2788 | [7 empty] | Not Submitted |  | 0 | 18000
A130 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3522 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A130 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 |  | 2210 | [7 empty] | Not Submitted |  | 0 | 18000
A130 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 |  | 3578 | [7 empty] | Not Submitted |  | 0 | 18000
A130 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3293 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A130 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A130 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2768 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A131 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3733 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A131 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3707 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A131 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2981 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A131 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A131 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2321 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A131 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3214 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A131 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3647 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A131 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2186 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A131 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2845 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A131 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2771 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A131 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A131 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3524 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A131 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A131 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A131 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3874 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A131 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A131 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2807 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A132 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3023 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A132 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 90 |  | 3284 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A132 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2300 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A132 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A132 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2519 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A132 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2754 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A132 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 3928 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 30400 | 7600
A132 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2187 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 8000 | 2000
A132 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3031 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A132 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2024 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 10800 | 1200
A132 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A132 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3142 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A132 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A132 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A132 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2453 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 8000 | 2000
A132 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A132 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3170 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A133 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3829 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 36000 | 9000
A133 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 2225 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A133 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2905 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A133 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A133 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2274 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A133 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2043 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 10000 | 0
A133 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2126 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 30400 | 7600
A133 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3745 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A133 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2795 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A133 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3619 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A133 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A133 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3313 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A133 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A133 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A133 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2796 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A133 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A133 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3066 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A134 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2969 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A134 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 100 |  | 3113 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 30400 | 7600
A134 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3667 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A134 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A134 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3526 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A134 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3832 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A134 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2507 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A134 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 80 |  | 3969 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 8000 | 2000
A134 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2774 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A134 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 80 |  | 3997 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A134 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A134 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2920 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 12000 | 0
A134 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A134 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A134 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2390 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A134 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A134 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3729 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A135 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2412 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A135 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A135 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2329 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A135 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A135 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3110 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A135 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 2616 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A135 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 3608 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 30400 | 7600
A135 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3088 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A135 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3708 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A135 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2826 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A135 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A135 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3209 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 12000 | 0
A135 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A135 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A135 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2879 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 8000 | 2000
A135 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A135 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2488 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A136 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2129 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A136 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A136 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 90 |  | 3377 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 30400 | 7600
A136 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A136 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2835 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A136 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3637 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A136 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2434 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A136 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 2679 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A136 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2394 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A136 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3100 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A136 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A136 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2195 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A136 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A136 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A136 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 3536 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A136 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A136 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2477 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A137 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3211 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 36000 | 9000
A137 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A137 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2598 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A137 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A137 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2660 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A137 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3415 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A137 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2628 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A137 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 3769 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A137 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2206 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 18000 | 0
A137 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3390 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A137 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A137 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2492 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A137 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A137 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A137 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2439 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A137 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A137 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2757 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A138 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3750 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A138 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A138 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3353 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 30400 | 7600
A138 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A138 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3161 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A138 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3710 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A138 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2379 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 30400 | 7600
A138 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2520 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9000 | 1000
A138 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3792 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A138 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2173 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A138 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A138 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2167 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A138 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A138 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A138 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3740 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 8000 | 2000
A138 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A138 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2498 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A139 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3154 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A139 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A139 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 3497 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 30400 | 7600
A139 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A139 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2673 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A139 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 90 |  | 3354 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 8000 | 2000
A139 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 100 |  | 2774 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 30400 | 7600
A139 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3705 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 8000 | 2000
A139 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3759 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A139 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2312 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A139 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A139 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2792 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A139 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A139 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A139 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 90 |  | 3829 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 8000 | 2000
A139 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A139 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3397 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A140 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2153 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A140 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A140 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 100 |  | 2205 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 38000 | 0
A140 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A140 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3615 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A140 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 3586 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 8000 | 2000
A140 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 90 |  | 2583 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 30400 | 7600
A140 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 100 |  | 3777 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A140 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2277 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A140 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3295 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A140 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A140 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2188 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A140 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A140 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A140 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 100 |  | 2890 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 8000 | 2000
A140 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A140 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2680 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A141 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2119 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A141 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A141 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A141 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A141 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3642 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A141 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 100 |  | 2263 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 8000 | 2000
A141 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A141 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 90 |  | 2543 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 8000 | 2000
A141 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3170 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A141 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2307 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A141 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A141 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3286 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A141 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A141 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A141 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A141 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A141 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2626 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A142 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3105 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A142 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A142 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A142 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A142 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 80 |  | 3962 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A142 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A142 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A142 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A142 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2534 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A142 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3465 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A142 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A142 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3944 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A142 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A142 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A142 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A142 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A142 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2016 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 18000 | 0
A143 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2475 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A143 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A143 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A143 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A143 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2818 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A143 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A143 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A143 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A143 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3604 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A143 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2375 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A143 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A143 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3785 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A143 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A143 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A143 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A143 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A143 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2021 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 18000 | 0
A144 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2008 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 45000 | 0
A144 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A144 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A144 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A144 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2862 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 16000 | 4000
A144 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A144 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A144 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A144 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2528 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A144 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2182 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A144 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A144 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2373 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A144 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A144 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A144 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A144 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A144 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2938 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A145 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2494 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A145 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A145 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A145 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A145 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3686 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A145 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A145 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A145 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A145 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3196 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A145 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2269 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A145 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A145 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3107 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A145 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A145 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A145 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A145 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A145 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2960 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A146 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2765 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A146 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A146 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A146 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A146 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2535 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A146 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A146 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A146 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A146 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 80 |  | 3985 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 14400 | 3600
A146 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2113 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A146 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A146 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2774 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A146 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A146 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A146 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A146 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A146 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2219 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A147 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3139 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A147 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A147 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A147 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A147 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 80 |  | 3999 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A147 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A147 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A147 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A147 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2556 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A147 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3597 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A147 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A147 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2317 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A147 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A147 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A147 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A147 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A147 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2609 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A148 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3704 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A148 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A148 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A148 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A148 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2306 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A148 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A148 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A148 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A148 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2140 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A148 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2307 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A148 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A148 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3194 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A148 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A148 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A148 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A148 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A148 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3050 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A149 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3066 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A149 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A149 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A149 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A149 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2161 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A149 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A149 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A149 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A149 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3856 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A149 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3561 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A149 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A149 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2165 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A149 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A149 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A149 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A149 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A149 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2826 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A150 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2804 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 36000 | 9000
A150 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A150 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A150 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A150 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2290 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A150 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A150 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A150 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A150 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2924 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A150 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3369 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A150 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A150 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2461 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A150 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A150 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A150 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A150 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A150 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3078 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A151 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2713 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A151 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A151 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A151 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A151 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 80 |  | 3972 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 16000 | 4000
A151 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A151 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A151 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A151 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2448 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A151 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2331 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A151 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A151 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3641 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A151 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A151 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A151 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A151 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A151 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2183 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A152 | Final Fix aluminium and Façade work | ARC | 1 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2568 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A152 | MEP 3rd Fix Electrical | MEP | 1 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A152 | MEP 3rd Fix Mechanical | MEP | 1 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A152 | Joinery Final Fix Doors | ARC | 1 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A152 | Final Paint Coat | ARC | 1 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3784 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A152 | Marble Threshold Final Fix | ARC | 1 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A152 | MEP 3rd Fix Plumping | MEP | 1 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A152 | Tiles Final Fix Wet Area | ARC | 1 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A152 | False ceiling Final Fix Wet Area | ARC | 1 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3563 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A152 | Mirror Final Fix | ARC | 1 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2540 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A152 | Vanity Counter Final Fix | ARC | 1 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A152 | Glass Shower Partition Final fix | ARC | 1 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3013 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A152 | Joinery Final Fix Laundry | ARC | 1 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A152 | Joinery Final Fix Kitchen | ARC | 1 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A152 | Tiles Final Fix Dry Area | ARC | 1 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A152 | Joinery Final Fix wardrobe | ARC | 1 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A152 | False ceiling Final Fix Dry Area | ARC | 1 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3174 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A201 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3792 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A201 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A201 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A201 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A201 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2915 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A201 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A201 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A201 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A201 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3751 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A201 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3282 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A201 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A201 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2853 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A201 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A201 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A201 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A201 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A201 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2180 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 14400 | 3600
A202 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2130 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A202 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A202 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A202 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A202 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2440 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A202 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A202 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A202 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A202 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3040 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A202 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3123 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A202 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A202 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3600 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A202 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A202 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A202 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A202 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A202 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2218 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A203 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3487 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A203 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A203 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A203 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A203 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2865 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A203 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A203 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A203 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A203 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2993 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A203 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2078 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 12000 | 0
A203 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A203 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3939 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A203 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A203 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A203 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A203 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A203 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3504 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A204 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2405 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 36000 | 9000
A204 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A204 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A204 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A204 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2261 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A204 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A204 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A204 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A204 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 2153 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A204 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2433 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A204 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A204 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3293 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A204 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A204 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A204 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A204 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A204 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2246 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A205 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3118 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 36000 | 9000
A205 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A205 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A205 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A205 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3743 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A205 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A205 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A205 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A205 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3798 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A205 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2259 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A205 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A205 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2925 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A205 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A205 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A205 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A205 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A205 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3649 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A206 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3396 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 36000 | 9000
A206 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A206 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A206 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A206 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2457 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A206 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A206 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A206 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A206 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3190 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A206 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3246 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A206 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A206 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2093 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 10800 | 1200
A206 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A206 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A206 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A206 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A206 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2523 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A207 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 2192 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 36000 | 9000
A207 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A207 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A207 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A207 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3753 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 16000 | 4000
A207 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A207 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A207 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A207 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3346 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A207 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2185 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A207 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A207 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2165 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A207 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A207 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A207 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A207 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A207 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2397 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A208 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3288 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A208 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A208 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A208 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A208 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2615 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A208 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A208 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A208 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A208 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3882 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A208 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3681 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A208 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A208 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3209 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 12000 | 0
A208 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A208 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A208 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A208 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A208 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3463 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 14400 | 3600
A209 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3862 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 36000 | 9000
A209 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A209 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A209 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A209 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2555 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A209 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A209 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A209 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A209 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3885 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A209 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2949 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A209 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A209 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2200 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 10800 | 1200
A209 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A209 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A209 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A209 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A209 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2546 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A210 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2033 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 45000 | 0
A210 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A210 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A210 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A210 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2817 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A210 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A210 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A210 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A210 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3591 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A210 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2796 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A210 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A210 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2399 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A210 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A210 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A210 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A210 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A210 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3011 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A211 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3674 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A211 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A211 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A211 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A211 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2828 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A211 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A211 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A211 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A211 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 90 |  | 3205 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16200 | 1800
A211 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2086 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 12000 | 0
A211 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A211 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3771 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A211 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A211 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A211 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A211 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A211 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2484 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A212 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3130 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A212 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A212 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A212 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A212 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3401 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A212 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A212 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A212 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A212 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3110 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A212 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2025 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 12000 | 0
A212 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A212 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3498 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A212 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A212 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A212 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A212 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A212 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2261 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A213 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 90 |  | 3636 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 36000 | 9000
A213 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A213 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A213 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A213 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2463 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 16000 | 4000
A213 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A213 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A213 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A213 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3491 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A213 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2304 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A213 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A213 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3457 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A213 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A213 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A213 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A213 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A213 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3128 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A214 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3794 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 36000 | 9000
A214 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A214 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A214 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A214 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3825 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A214 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A214 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A214 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A214 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2202 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 18000 | 0
A214 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2124 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A214 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A214 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3406 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A214 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A214 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A214 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A214 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A214 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2321 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A215 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 2501 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 36000 | 9000
A215 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A215 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A215 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A215 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2787 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 16000 | 4000
A215 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A215 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A215 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A215 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2043 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 18000 | 0
A215 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2575 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A215 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A215 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3547 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A215 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A215 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A215 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A215 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A215 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 2141 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 14400 | 3600
A216 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3555 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 36000 | 9000
A216 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A216 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A216 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A216 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2948 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A216 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A216 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A216 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A216 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3714 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A216 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2964 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A216 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A216 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2184 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A216 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A216 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A216 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A216 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A216 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3054 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A217 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 100 |  | 3474 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 36000 | 9000
A217 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A217 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A217 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A217 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3246 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 16000 | 4000
A217 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A217 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A217 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A217 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3807 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A217 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3069 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A217 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A217 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2791 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A217 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A217 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A217 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A217 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A217 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2110 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A218 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A218 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A218 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A218 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A218 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3356 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 16000 | 4000
A218 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A218 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A218 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A218 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3267 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A218 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2236 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A218 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A218 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2809 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A218 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A218 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A218 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A218 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A218 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2605 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A219 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A219 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A219 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A219 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A219 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2650 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A219 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A219 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A219 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A219 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2387 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A219 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3202 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 12000 | 0
A219 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A219 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2627 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A219 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A219 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A219 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A219 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A219 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 90 |  | 3308 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 14400 | 3600
A220 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A220 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A220 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A220 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A220 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3020 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 20000 | 0
A220 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A220 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A220 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A220 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3592 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A220 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2227 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A220 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A220 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2377 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A220 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A220 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A220 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A220 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A220 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3553 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A221 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A221 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A221 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A221 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A221 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3296 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A221 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A221 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A221 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A221 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3131 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 14400 | 3600
A221 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2623 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A221 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A221 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3008 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A221 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A221 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A221 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A221 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A221 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3865 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A222 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A222 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A222 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A222 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A222 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2276 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 16000 | 4000
A222 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A222 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A222 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A222 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3644 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 14400 | 3600
A222 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3311 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A222 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A222 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2326 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A222 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A222 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A222 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A222 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A222 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2812 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A223 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A223 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A223 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A223 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A223 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 2396 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 16000 | 4000
A223 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A223 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A223 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A223 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 2574 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A223 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3844 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A223 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A223 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2055 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 12000 | 0
A223 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A223 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A223 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A223 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A223 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3886 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 14400 | 3600
A224 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A224 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A224 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A224 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A224 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 2388 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 16000 | 4000
A224 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A224 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A224 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A224 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3339 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 14400 | 3600
A224 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2830 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A224 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A224 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2445 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A224 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A224 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A224 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A224 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A224 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 2546 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 14400 | 3600
A225 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A225 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A225 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A225 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A225 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 90 |  | 3517 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 16000 | 4000
A225 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A225 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A225 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A225 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3736 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 14400 | 3600
A225 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3134 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A225 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A225 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2064 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 10800 | 1200
A225 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A225 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A225 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A225 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A225 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3027 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 14400 | 3600
A226 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A226 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A226 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A226 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A226 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3051 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 16000 | 4000
A226 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A226 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A226 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A226 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 100 |  | 3150 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A226 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2706 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A226 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A226 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3884 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A226 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A226 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A226 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A226 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A226 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 100 |  | 3087 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 14400 | 3600
A227 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A227 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A227 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A227 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 100 |  | 3879 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 16000 | 4000
A227 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A227 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A227 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A227 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3118 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A227 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3120 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 12000 | 0
A227 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A227 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A227 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A228 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A228 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A228 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A228 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A228 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A228 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A228 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2878 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A228 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3954 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A228 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A228 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A228 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A229 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A229 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A229 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A229 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A229 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A229 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A229 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2855 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A229 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3133 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A229 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A229 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A229 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A230 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A230 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A230 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A230 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A230 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A230 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A230 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2606 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A230 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2328 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A230 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A230 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A230 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A231 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A231 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A231 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A231 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A231 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A231 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A231 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2892 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A231 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2723 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A231 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A231 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A231 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A232 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A232 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A232 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A232 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A232 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A232 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A232 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3821 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A232 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2259 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A232 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A232 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A232 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A233 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A233 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A233 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A233 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A233 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A233 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A233 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2971 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A233 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3470 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A233 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A233 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A233 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A234 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A234 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A234 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A234 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A234 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A234 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A234 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2639 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A234 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3569 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A234 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A234 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A234 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A235 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A235 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A235 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A235 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A235 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A235 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A235 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3416 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A235 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3213 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A235 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A235 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A235 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A236 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A236 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A236 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A236 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A236 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A236 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A236 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2560 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A236 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3237 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A236 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A236 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A236 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A237 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A237 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A237 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A237 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A237 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A237 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A237 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2002 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 12000 | 0
A237 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2530 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A237 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A237 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A237 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A238 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A238 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A238 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A238 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A238 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A238 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A238 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2011 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 12000 | 0
A238 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3928 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A238 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A238 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A238 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A239 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A239 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A239 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A239 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A239 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A239 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A239 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3320 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 12000 | 0
A239 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3009 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A239 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A239 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A239 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A240 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A240 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A240 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A240 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A240 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A240 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A240 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3337 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A240 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2190 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A240 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A240 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A240 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A241 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A241 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A241 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A241 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A241 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A241 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A241 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2761 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A241 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2533 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A241 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A241 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A241 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A242 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A242 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A242 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A242 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A242 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A242 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A242 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 80 |  | 3988 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A242 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3132 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A242 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A242 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A242 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A243 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A243 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A243 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A243 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A243 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A243 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A243 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2250 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A243 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2970 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A243 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A243 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A243 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A244 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A244 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A244 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A244 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A244 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A244 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A244 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2151 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A244 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2559 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A244 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A244 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A244 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A245 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A245 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A245 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A245 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A245 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A245 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A245 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2652 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A245 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3867 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A245 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A245 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A245 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A246 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A246 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A246 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A246 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A246 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A246 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A246 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 3253 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A246 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3417 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A246 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A246 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A246 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A247 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A247 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A247 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A247 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A247 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A247 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A247 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2038 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 12000 | 0
A247 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2419 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A247 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A247 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A247 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A248 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A248 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A248 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A248 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A248 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A248 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A248 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2101 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A248 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2532 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A248 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A248 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A248 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A249 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A249 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A249 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A249 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A249 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A249 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A249 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3222 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A249 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3137 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A249 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A249 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A249 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A250 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A250 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A250 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A250 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A250 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A250 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A250 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2238 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A250 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2856 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A250 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A250 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A250 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A251 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A251 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A251 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A251 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A251 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A251 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A251 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2040 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 12000 | 0
A251 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2152 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A251 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A251 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A251 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Final Fix aluminium and Façade work | ARC | 2 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A252 | MEP 3rd Fix Electrical | MEP | 2 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A252 | MEP 3rd Fix Mechanical | MEP | 2 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A252 | Joinery Final Fix Doors | ARC | 2 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Final Paint Coat | ARC | 2 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A252 | Marble Threshold Final Fix | ARC | 2 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A252 | MEP 3rd Fix Plumping | MEP | 2 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A252 | Tiles Final Fix Wet Area | ARC | 2 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A252 | False ceiling Final Fix Wet Area | ARC | 2 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Mirror Final Fix | ARC | 2 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2110 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A252 | Vanity Counter Final Fix | ARC | 2 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Glass Shower Partition Final fix | ARC | 2 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3060 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A252 | Joinery Final Fix Laundry | ARC | 2 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Joinery Final Fix Kitchen | ARC | 2 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | Tiles Final Fix Dry Area | ARC | 2 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A252 | Joinery Final Fix wardrobe | ARC | 2 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A252 | False ceiling Final Fix Dry Area | ARC | 2 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A301 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A301 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A301 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A301 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A301 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A301 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A301 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 90 |  | 2674 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A301 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3419 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A301 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A301 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A301 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A302 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A302 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A302 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A302 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A302 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A302 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A302 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 3062 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A302 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2678 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A302 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A302 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A302 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A303 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A303 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A303 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A303 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A303 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A303 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A303 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2877 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A303 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2626 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A303 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A303 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A303 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A304 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A304 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A304 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A304 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A304 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A304 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A304 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 100 |  | 2242 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A304 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3517 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A304 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A304 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A304 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A305 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A305 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A305 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A305 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A305 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A305 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A305 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A305 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3466 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A305 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A305 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A305 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A306 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A306 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A306 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A306 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A306 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A306 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A306 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A306 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2703 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A306 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A306 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A306 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A307 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A307 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A307 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A307 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A307 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A307 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A307 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A307 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3512 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A307 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A307 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A307 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A308 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A308 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A308 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A308 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A308 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A308 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A308 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A308 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3380 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A308 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A308 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A308 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A309 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A309 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A309 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A309 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A309 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A309 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A309 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A309 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3508 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A309 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A309 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A309 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A310 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A310 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A310 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A310 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A310 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A310 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A310 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A310 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2510 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A310 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A310 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A310 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A311 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A311 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A311 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A311 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A311 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A311 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A311 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A311 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2869 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A311 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A311 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A311 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A312 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A312 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A312 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A312 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A312 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A312 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A312 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A312 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3064 |  |  |  |  | 2022-11-06 | 2022-11-16 | C | Rejected |  | 9600 | 2400
A312 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A312 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A312 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A313 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A313 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A313 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A313 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A313 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A313 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A313 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A313 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3531 |  |  |  |  | 2022-11-06 | 2022-11-16 | B | Approved as Noted |  | 9600 | 2400
A313 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A313 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A313 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A314 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A314 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A314 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A314 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A314 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A314 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A314 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A314 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2590 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A314 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A314 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A314 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A315 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A315 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A315 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A315 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A315 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A315 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A315 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A315 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3263 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A315 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A315 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A315 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A316 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A316 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A316 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A316 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A316 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A316 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A316 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A316 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3975 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A316 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A316 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A316 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A317 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A317 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A317 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A317 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A317 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A317 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A317 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A317 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2740 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A317 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A317 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A317 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A318 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A318 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A318 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A318 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A318 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 38000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 38000
A318 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A318 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A318 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2683 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A318 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A318 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A318 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A319 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A319 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A319 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A319 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A319 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A319 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A319 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A319 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2689 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A319 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A319 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A319 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A320 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A320 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A320 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A320 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A320 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A320 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A320 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A320 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2544 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A320 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A320 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A320 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A321 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A321 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A321 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A321 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A321 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A321 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A321 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A321 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 80 |  | 3961 |  |  |  |  | 2022-11-06 |  | UR | Under Review |  | 9600 | 2400
A321 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A321 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A321 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A322 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A322 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A322 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A322 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A322 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A322 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A322 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A322 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3452 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A322 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A322 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A322 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A323 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A323 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A323 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A323 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A323 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A323 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A323 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A323 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2607 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A323 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A323 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A323 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A324 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A324 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A324 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A324 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A324 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A324 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A324 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A324 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 3750 |  |  |  |  | 2022-11-06 | 2022-11-14 | C | Rejected |  | 9600 | 2400
A324 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A324 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A324 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A325 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A325 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A325 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A325 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A325 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A325 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A325 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A325 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2357 |  |  |  |  | 2022-11-06 | 2022-11-13 | C | Rejected |  | 9600 | 2400
A325 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A325 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A325 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A326 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A326 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A326 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A326 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A326 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A326 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A326 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A326 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3139 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A326 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A326 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A326 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A327 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A327 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A327 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A327 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A327 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A327 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A327 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A327 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2506 |  |  |  |  | 2022-11-06 | 2022-11-13 | B | Approved as Noted |  | 9600 | 2400
A327 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A327 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A327 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A328 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A328 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A328 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A328 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A328 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A328 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A328 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A328 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2038 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 12000 | 0
A328 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A328 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A328 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A329 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A329 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A329 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A329 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A329 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A329 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A329 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A329 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2619 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A329 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A329 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A329 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A330 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A330 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A330 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A330 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A330 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A330 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A330 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A330 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3656 |  |  |  |  | 2022-11-06 | 2022-11-13 | A | Approved |  | 9600 | 2400
A330 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A330 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A330 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A331 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A331 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A331 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A331 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A331 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A331 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A331 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A331 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2645 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A331 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A331 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A331 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A332 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A332 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A332 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A332 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A332 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A332 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A332 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A332 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3781 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A332 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A332 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A332 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A333 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A333 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A333 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A333 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A333 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A333 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A333 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A333 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 2453 |  |  |  |  | 2022-11-06 | 2022-11-15 | B | Approved as Noted |  | 9600 | 2400
A333 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A333 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A333 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A334 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A334 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A334 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A334 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A334 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A334 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A334 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A334 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3014 |  |  |  |  | 2022-11-06 | 2022-11-14 | A | Approved |  | 9600 | 2400
A334 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A334 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A334 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A335 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A335 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A335 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A335 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A335 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A335 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A335 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A335 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3151 |  |  |  |  | 2022-11-06 | 2022-11-16 | A | Approved |  | 9600 | 2400
A335 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A335 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A335 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A336 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A336 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A336 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A336 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A336 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A336 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A336 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A336 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3478 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A336 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A336 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A336 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A337 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A337 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A337 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A337 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A337 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A337 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A337 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A337 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3885 |  |  |  |  | 2022-11-06 | 2022-11-15 | A | Approved |  | 9600 | 2400
A337 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A337 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A337 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A338 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A338 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A338 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A338 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A338 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A338 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A338 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A338 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 100 |  | 3248 |  |  |  |  | 2022-11-06 | 2022-11-14 | B | Approved as Noted |  | 9600 | 2400
A338 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A338 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A338 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A339 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A339 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A339 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A339 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A339 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A339 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A339 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A339 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 90 |  | 2959 |  |  |  |  | 2022-11-06 | 2022-11-15 | C | Rejected |  | 9600 | 2400
A339 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A339 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A339 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A340 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A340 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A340 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A340 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A340 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A340 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A340 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A340 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A340 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A340 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A340 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A341 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A341 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A341 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A341 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A341 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A341 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A341 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A341 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A341 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A341 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A341 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A342 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A342 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A342 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A342 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A342 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A342 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A342 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A342 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A342 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A342 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A342 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A343 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A343 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A343 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A343 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A343 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A343 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A343 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A343 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A343 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A343 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A343 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A344 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A344 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A344 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A344 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A344 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A344 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A344 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A344 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A344 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A344 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A344 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A345 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A345 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A345 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A345 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A345 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A345 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A345 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A345 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A345 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A345 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A345 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A346 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A346 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A346 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A346 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A346 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A346 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A346 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A346 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A346 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A346 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A346 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A347 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A347 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A347 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A347 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A347 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A347 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A347 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A347 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A347 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A347 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A347 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A348 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A348 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A348 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A348 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A348 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A348 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A348 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A348 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A348 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A348 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A348 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A349 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A349 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A349 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A349 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A349 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A349 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A349 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A349 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A349 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A349 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A349 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A350 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A350 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A350 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A350 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A350 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A350 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A350 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A350 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A350 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A350 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A350 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A351 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A351 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A351 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A351 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A351 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A351 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A351 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A351 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A351 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A351 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A351 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Final Fix aluminium and Façade work | ARC | 3 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A352 | MEP 3rd Fix Electrical | MEP | 3 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A352 | MEP 3rd Fix Mechanical | MEP | 3 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A352 | Joinery Final Fix Doors | ARC | 3 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Final Paint Coat | ARC | 3 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A352 | Marble Threshold Final Fix | ARC | 3 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A352 | MEP 3rd Fix Plumping | MEP | 3 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A352 | Tiles Final Fix Wet Area | ARC | 3 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A352 | False ceiling Final Fix Wet Area | ARC | 3 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Mirror Final Fix | ARC | 3 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A352 | Vanity Counter Final Fix | ARC | 3 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Glass Shower Partition Final fix | ARC | 3 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A352 | Joinery Final Fix Laundry | ARC | 3 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Joinery Final Fix Kitchen | ARC | 3 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | Tiles Final Fix Dry Area | ARC | 3 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A352 | Joinery Final Fix wardrobe | ARC | 3 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A352 | False ceiling Final Fix Dry Area | ARC | 3 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A401 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A401 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A401 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A401 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A401 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A401 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A401 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A401 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A401 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A401 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A401 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A402 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A402 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A402 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A402 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A402 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A402 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A402 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A402 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A402 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A402 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A402 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A403 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A403 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A403 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A403 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A403 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A403 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A403 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A403 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A403 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A403 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A403 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A404 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A404 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A404 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A404 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A404 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A404 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A404 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A404 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A404 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A404 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A404 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A405 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A405 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A405 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A405 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A405 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A405 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A405 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A405 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A405 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A405 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A405 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A406 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A406 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A406 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A406 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A406 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A406 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A406 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A406 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A406 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A406 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A406 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A407 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A407 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A407 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A407 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A407 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A407 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A407 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A407 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A407 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A407 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A407 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A408 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A408 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A408 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A408 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A408 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A408 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A408 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A408 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A408 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A408 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A408 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A409 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A409 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A409 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A409 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A409 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A409 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A409 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A409 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A409 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A409 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A409 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A410 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A410 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A410 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A410 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A410 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A410 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A410 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A410 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A410 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A410 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A410 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A411 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A411 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A411 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A411 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A411 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A411 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A411 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A411 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A411 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A411 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A411 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A412 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A412 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A412 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A412 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A412 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A412 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A412 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A412 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A412 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A412 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A412 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A413 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A413 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A413 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A413 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A413 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A413 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A413 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A413 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A413 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A413 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A413 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A414 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A414 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A414 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A414 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A414 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A414 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A414 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A414 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A414 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A414 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A414 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A415 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A415 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A415 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A415 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A415 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A415 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A415 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A415 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A415 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A415 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A415 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A416 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A416 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A416 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A416 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A416 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A416 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A416 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A416 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A416 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A416 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A416 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A417 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A417 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A417 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A417 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A417 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A417 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A417 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A417 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A417 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A417 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A417 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A418 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A418 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A418 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A418 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A418 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A418 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A418 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A418 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A418 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A418 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A418 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A419 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A419 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A419 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A419 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A419 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A419 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A419 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A419 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A419 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A419 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A419 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A420 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A420 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A420 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A420 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A420 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A420 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A420 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A420 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A420 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A420 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A420 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A421 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A421 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A421 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A421 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A421 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A421 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A421 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A421 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A421 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A421 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A421 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A422 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A422 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A422 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A422 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A422 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A422 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A422 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A422 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A422 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A422 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A422 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A423 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A423 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A423 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A423 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A423 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A423 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A423 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A423 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A423 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A423 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A423 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A424 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A424 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A424 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A424 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A424 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A424 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A424 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A424 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A424 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A424 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A424 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A425 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A425 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A425 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A425 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A425 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A425 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A425 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A425 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A425 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A425 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A425 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A426 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A426 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A426 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A426 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A426 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A426 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A426 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A426 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A426 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A426 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A426 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A427 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A427 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A427 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A427 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A427 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A427 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A427 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A427 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A427 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A427 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A427 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A428 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A428 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A428 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A428 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A428 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A428 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A428 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A428 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A428 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A428 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A428 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A429 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A429 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A429 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A429 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A429 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A429 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A429 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A429 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A429 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A429 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A429 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A430 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A430 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A430 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A430 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A430 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A430 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A430 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A430 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A430 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A430 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A430 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A431 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A431 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A431 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A431 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A431 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A431 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A431 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A431 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A431 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A431 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A431 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A432 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A432 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A432 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A432 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A432 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A432 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A432 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A432 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A432 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A432 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A432 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A433 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A433 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A433 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A433 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A433 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A433 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A433 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A433 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A433 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A433 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A433 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A434 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A434 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A434 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A434 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A434 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A434 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A434 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A434 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A434 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A434 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A434 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A435 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A435 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A435 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A435 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A435 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A435 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A435 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A435 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A435 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A435 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A435 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A436 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A436 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A436 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A436 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A436 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A436 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A436 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A436 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A436 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A436 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A436 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A437 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A437 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A437 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A437 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A437 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A437 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A437 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A437 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A437 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A437 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A437 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A438 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A438 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A438 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A438 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A438 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A438 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A438 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A438 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A438 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A438 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A438 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A439 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A439 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A439 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A439 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A439 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A439 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A439 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A439 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A439 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A439 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A439 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A440 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A440 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A440 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A440 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A440 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A440 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A440 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A440 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A440 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A440 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A440 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A441 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A441 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A441 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A441 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A441 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A441 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A441 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A441 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A441 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A441 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A441 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A442 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A442 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A442 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A442 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A442 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A442 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A442 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A442 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A442 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A442 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A442 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A443 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A443 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A443 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A443 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A443 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A443 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A443 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A443 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A443 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A443 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A443 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A444 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A444 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A444 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A444 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A444 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A444 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A444 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A444 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A444 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A444 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A444 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A445 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A445 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A445 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A445 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A445 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A445 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A445 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A445 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A445 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A445 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A445 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A446 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A446 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A446 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A446 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A446 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A446 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A446 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A446 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A446 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A446 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A446 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A447 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A447 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A447 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A447 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A447 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A447 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A447 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A447 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A447 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A447 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A447 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A448 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A448 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A448 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A448 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A448 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A448 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A448 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A448 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A448 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A448 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A448 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A449 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A449 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A449 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A449 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A449 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A449 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A449 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A449 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A449 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A449 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A449 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A450 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A450 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A450 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A450 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A450 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A450 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A450 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A450 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A450 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A450 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A450 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A451 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A451 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A451 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A451 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A451 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A451 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A451 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A451 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A451 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A451 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A451 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Final Fix aluminium and Façade work | ARC | 4 | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A452 | MEP 3rd Fix Electrical | MEP | 4 | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A452 | MEP 3rd Fix Mechanical | MEP | 4 | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A452 | Joinery Final Fix Doors | ARC | 4 | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Final Paint Coat | ARC | 4 | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A452 | Marble Threshold Final Fix | ARC | 4 | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A452 | MEP 3rd Fix Plumping | MEP | 4 | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A452 | Tiles Final Fix Wet Area | ARC | 4 | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A452 | False ceiling Final Fix Wet Area | ARC | 4 | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Mirror Final Fix | ARC | 4 | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A452 | Vanity Counter Final Fix | ARC | 4 | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Glass Shower Partition Final fix | ARC | 4 | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A452 | Joinery Final Fix Laundry | ARC | 4 | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Joinery Final Fix Kitchen | ARC | 4 | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | Tiles Final Fix Dry Area | ARC | 4 | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A452 | Joinery Final Fix wardrobe | ARC | 4 | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A452 | False ceiling Final Fix Dry Area | ARC | 4 | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R01 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R01 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R01 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R01 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R01 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R01 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R01 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R01 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R01 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R01 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R01 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R02 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R02 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R02 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R02 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R02 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R02 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R02 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R02 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R02 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R02 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R02 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R03 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R03 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R03 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R03 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R03 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R03 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R03 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R03 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R03 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R03 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R03 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R04 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R04 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R04 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R04 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R04 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R04 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R04 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R04 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R04 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R04 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R04 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R05 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R05 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R05 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R05 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R05 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R05 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R05 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R05 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R05 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R05 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R05 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R06 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R06 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R06 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R06 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R06 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R06 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R06 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R06 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R06 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R06 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R06 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R07 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R07 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R07 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R07 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R07 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R07 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R07 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R07 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R07 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R07 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R07 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R08 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R08 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R08 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R08 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R08 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R08 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R08 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R08 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R08 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R08 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R08 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R09 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R09 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R09 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R09 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R09 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R09 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R09 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R09 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R09 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R09 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R09 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R10 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R10 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R10 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R10 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R10 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R10 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R10 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R10 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R10 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R10 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R10 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R11 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R11 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R11 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R11 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R11 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R11 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R11 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R11 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R11 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R11 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R11 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R12 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R12 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R12 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R12 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R12 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R12 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R12 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R12 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R12 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R12 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R12 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R13 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R13 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R13 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R13 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R13 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R13 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R13 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R13 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R13 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R13 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R13 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R14 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R14 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R14 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R14 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R14 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R14 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R14 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R14 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R14 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R14 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R14 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R15 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R15 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R15 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R15 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R15 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R15 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R15 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R15 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R15 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R15 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R15 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Final Fix aluminium and Façade work | ARC | 5R | FLR | AL | A01 | [5 empty] | 45000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 45000
A5R16 | MEP 3rd Fix Electrical | MEP | 5R | FLR | EL | A02 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R16 | MEP 3rd Fix Mechanical | MEP | 5R | FLR | MC | A03 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R16 | Joinery Final Fix Doors | ARC | 5R | FLR | JN | A04 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Final Paint Coat | ARC | 5R | FLR | PN | A05 | [5 empty] | 20000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 20000
A5R16 | Marble Threshold Final Fix | ARC | 5R | FLR | TL | A06 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R16 | MEP 3rd Fix Plumping | MEP | 5R | WET | MC | A07 | [5 empty] | 40000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 40000
A5R16 | Tiles Final Fix Wet Area | ARC | 5R | WET | TL | A08 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R16 | False ceiling Final Fix Wet Area | ARC | 5R | WET | FC | A09 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Mirror Final Fix | ARC | 5R | TOI | MR | A10 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R16 | Vanity Counter Final Fix | ARC | 5R | TOI | JN | A11 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Glass Shower Partition Final fix | ARC | 5R | TOI | GP | A12 | [5 empty] | 12000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 12000
A5R16 | Joinery Final Fix Laundry | ARC | 5R | LAU | JN | A13 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Joinery Final Fix Kitchen | ARC | 5R | KIT | JN | A14 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | Tiles Final Fix Dry Area | ARC | 5R | DRY | TL | A15 | [5 empty] | 10000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 10000
A5R16 | Joinery Final Fix wardrobe | ARC | 5R | DRY | JN | A16 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
A5R16 | False ceiling Final Fix Dry Area | ARC | 5R | DRY | FC | A17 | [5 empty] | 18000 | [13 empty] | 0 | [9 empty] | Not Submitted |  | 0 | 18000
Note on H1: Hafiz: What if two BOQ items installaed together? Same as trade? Comment applicable for all BOQ related columns